## Slide 1: ICTs for Sustainable Development
      Objectives and deliverables
      Resource requirements
      Pitfalls
      Impact
      Lessons
Agenda
© Education Development Center

## Slide 2
Multimedia Training in the Philippines
© Education Development Center

## Slide 3: DOH Multimedia Center of Excellence
Objectives
Create a Multimedia Center
Train DOH staff
Develop two CD-ROMs
  Family Planning Counseling
  Screen blood for HIV/AIDS
Formulate a business plan
© Education Development Center

## Slide 4: Deliverables: Create a Center
We’re trainers, not contractors
Began with a concrete shell
Built the entire center, with all facilities
© Education Development Center

## Slide 5: Deliverables: Two CD-ROMs
“Protecting Our Blood Supply”
Helps ensure quality control
Useful for trainees with differing skill levels
Is an effective training vehicle
Expands training reach
Reduces the cost of training
© Education Development Center

## Slide 6: Deliverables: Two CD-ROMs
“Family Planning Counseling for Couples”
Serves multiple audiences
Is effective for novice ICT users -- and they enjoy using it
Expands training reach
Establishes consistency
© Education Development Center

## Slide 7: Deliverables: Train DOH Staff
Created a multi-skilled MMCE team
Audio production
Video production
Graphic design for print materials
Ability to create multimedia CD-ROMs
Management skills
© Education Development Center

## Slide 8: Deliverables: A Business Plan
Value was psychological vs. financial
Demonstrated that the MMCE could spin off successfully
Instilled confidence
Elicited respect from senior management
Provided knowledge of “the competition”
© Education Development Center

## Slide 9: Resources Required: Human
Key MMCE technical staff requirements
Interest
Innate talent and intelligence
Ability to work as a team member
Content expertise
© Education Development Center

## Slide 10: Resources Required: Human
Key management requirements
Commitment from at least some sr. management
Leadership within MMCE
“Business management” skills
© Education Development Center

## Slide 11: Resources Required: Technological
Typical technology requirements
Microcomputers and modems
Knowledgeable support services (Apple vs. Compaq)
Sources for an array of equipment
Infrastructure (electricity, phone lines)
Internet Services (ISPs)
© Education Development Center

## Slide 12: Resources Required: Financial
The project does not control key financial resources
Adequate salaries for trained staff
Sufficient resources to procure and update equipment in the long-term
Financial support for equipment in delivery centers
© Education Development Center

## Slide 13: Impact
MMCE has survived and been successful
Offers skills that DOH values
  Improved print communications
  High quality design and production capacity
Can develop good quality CD-ROMs
Can learn new technologies and applications
© Education Development Center

## Slide 14: Pitfalls
Most pitfalls relate to time constraints
Recognize differences in “level of quality” requirements
Difficulties rolling out the CD-ROMs after policy or political changes
© Education Development Center

## Slide 15: Lessons
CD-ROMs can have a role, when:
Quality and consistency are crucial
Cost of classroom training is high
Classroom training is not feasible
A management and dissemination system can be established
© Education Development Center

## Slide 16: Lessons
Success factors
Obtain support from “near the top”
Develop internal leadership
Build a strong, confident team
  Talent can substitute for background experience
© Education Development Center

## Slide 17: Lessons
Success factors, continued
Establish strong relationships
Be prepared for conflict between international and local experts
Determine the basic, ongoing value proposition
  Ensure strong skills in “low tech” communications
© Education Development Center

## Slide 18: Frustrations Without Lessons
Knowing the lesson Bringing about change
Donors talk cooperation but walk in isolation
Political shifts can scuttle long-term plans
Sexy technology trumps sensible technology
Donor ADD limits management and dissemination systems roll-out
© Education Development Center